## Issue Navigator
Nyckel | Sammanfattning | Beskrivning | Bevakningar | Issue color | Lösning | Löst | P | Personer som arbetar på denna Task | Projekt | Rapportör | Senast visade | Skapad | Skapad av | Status | Status Category | Status Category Changed | T | Uppdaterad | Ärendeägare | Överordnad
GG-1 | Planera MVP |  | 1 |  | Klart | 2023-02-08 09:15 | Medium |  | 4chat | M0ller | 2023-01-19 16:18 | 2023-01-13 15:25 | M0ller | Klart | Klart | 2023-02-08 09:15 | Uppgift | 2023-02-08 09:15
GG-3 | Preppa kontinuerligt realeses |  | 1 |  | Klart | 2023-02-08 09:15 | Medium |  | 4chat | M0ller | 2023-01-19 16:25 | 2023-01-13 15:27 | M0ller | Klart | Klart | 2023-02-08 09:15 | Uppgift | 2023-02-08 09:15
GG-32 | Allow users to create new chat rooms by providing a name |  | 1 |  | Klart | 2023-02-15 09:54 | Medium | [{self=https://4chat.atlassian.net/rest/api/2/user?accountId=624ab2968678e900705d1178, accountId=624ab2968678e900705d1178, avatarUrls={48x48=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624ab2968678e900705d1178/05988c55-ba76-4ea1-8930-521ec9b7ce1a/48, 24x24=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624ab2968678e900705d1178/05988c55-ba76-4ea1-8930-521ec9b7ce1a/24, 16x16=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624ab2968678e900705d1178/05988c55-ba76-4ea1-8930-521ec9b7ce1a/16, 32x32=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624ab2968678e900705d1178/05988c55-ba76-4ea1-8930-521ec9b7ce1a/32}, displayName=barkat alirahimi, active=true, timeZone=Europe/Stockholm, accountType=atlassian}, {self=https://4chat.atlassian.net/rest/api/2/user?accountId=626f8f8da1de4100684ecb89, accountId=626f8f8da1de4100684ecb89, avatarUrls={48x48=https://secure.gravatar.com/avatar/739adc12ae3d7abb23402f074af78ffb?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FMH-3.png, 24x24=https://secure.gravatar.com/avatar/739adc12ae3d7abb23402f074af78ffb?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FMH-3.png, 16x16=https://secure.gravatar.com/avatar/739adc12ae3d7abb23402f074af78ffb?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FMH-3.png, 32x32=https://secure.gravatar.com/avatar/739adc12ae3d7abb23402f074af78ffb?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FMH-3.png}, displayName=Måns Hammarsntrad, active=true, timeZone=Europe/Stockholm, accountType=atlassian}] | 4chat | sanjin.lihovic | 2023-02-15 09:54 | 2023-01-18 10:48 | sanjin.lihovic | Klart | Klart | 2023-02-15 09:54 | Uppgift | 2023-02-15 09:55 | sanjin.lihovic | GG-27 Public and private chat rooms (Epic)
GG-33 | Allow users to join existing chat rooms browsing a list of available chat rooms |  | 1 |  | Klart | 2023-02-15 09:54 | Medium | [{self=https://4chat.atlassian.net/rest/api/2/user?accountId=5f5201acfdc3f5003f4f396d, accountId=5f5201acfdc3f5003f4f396d, avatarUrls={48x48=https://secure.gravatar.com/avatar/639a996f196a64b934573ac4b854ed59?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FSN-3.png, 24x24=https://secure.gravatar.com/avatar/639a996f196a64b934573ac4b854ed59?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FSN-3.png, 16x16=https://secure.gravatar.com/avatar/639a996f196a64b934573ac4b854ed59?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FSN-3.png, 32x32=https://secure.gravatar.com/avatar/639a996f196a64b934573ac4b854ed59?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FSN-3.png}, displayName=Sami Nasufovski, active=true, timeZone=Europe/Stockholm, accountType=atlassian}, {self=https://4chat.atlassian.net/rest/api/2/user?accountId=624add67699649006ae92359, accountId=624add67699649006ae92359, avatarUrls={48x48=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624add67699649006ae92359/dc844e2b-b121-4a68-9e53-47088343c533/48, 24x24=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624add67699649006ae92359/dc844e2b-b121-4a68-9e53-47088343c533/24, 16x16=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624add67699649006ae92359/dc844e2b-b121-4a68-9e53-47088343c533/16, 32x32=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624add67699649006ae92359/dc844e2b-b121-4a68-9e53-47088343c533/32}, displayName=sanjin.lihovic, active=true, timeZone=Europe/Stockholm, accountType=atlassian}] | 4chat | sanjin.lihovic | 2023-02-15 09:54 | 2023-01-18 10:48 | sanjin.lihovic | Klart | Klart | 2023-02-15 09:54 | Uppgift | 2023-02-15 09:54 | sanjin.lihovic | GG-27 Public and private chat rooms (Epic)
GG-35 | Implement the ability to leave a chat room |  | 1 |  | Klart | 2023-02-15 09:55 | Medium |  | 4chat | sanjin.lihovic |  | 2023-01-18 10:48 | sanjin.lihovic | Klart | Klart | 2023-02-15 09:55 | Uppgift | 2023-02-15 09:55 | sanjin.lihovic | GG-27 Public and private chat rooms (Epic)
GG-37 | Use a technology such as WebSockets to establish a real-time connection between the client and server |  | 1 |  | Klart | 2023-02-06 10:37 | Medium |  | 4chat | sanjin.lihovic | 2023-02-03 11:03 | 2023-01-18 10:48 | sanjin.lihovic | Klart | Klart | 2023-02-06 10:37 | Uppgift | 2023-02-06 10:37 | Sami Nasufovski | GG-36 Real-time messaging (Epic)
GG-39 | Allow users to send and receive messages in real-time |  | 1 |  | Klart | 2023-02-06 11:12 | Medium | [{self=https://4chat.atlassian.net/rest/api/2/user?accountId=624ac240258562006fa61ce3, accountId=624ac240258562006fa61ce3, avatarUrls={48x48=https://secure.gravatar.com/avatar/c9124722ce9863b6b54ec2457a8b199d?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FH-3.png, 24x24=https://secure.gravatar.com/avatar/c9124722ce9863b6b54ec2457a8b199d?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FH-3.png, 16x16=https://secure.gravatar.com/avatar/c9124722ce9863b6b54ec2457a8b199d?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FH-3.png, 32x32=https://secure.gravatar.com/avatar/c9124722ce9863b6b54ec2457a8b199d?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FH-3.png}, displayName=Hannes, active=true, timeZone=Europe/Stockholm, accountType=atlassian}, {self=https://4chat.atlassian.net/rest/api/2/user?accountId=624d3ebbad6b7e006aa8e709, accountId=624d3ebbad6b7e006aa8e709, avatarUrls={48x48=https://secure.gravatar.com/avatar/76357a8ddb2f28a045762b6633b21cde?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FJE-2.png, 24x24=https://secure.gravatar.com/avatar/76357a8ddb2f28a045762b6633b21cde?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FJE-2.png, 16x16=https://secure.gravatar.com/avatar/76357a8ddb2f28a045762b6633b21cde?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FJE-2.png, 32x32=https://secure.gravatar.com/avatar/76357a8ddb2f28a045762b6633b21cde?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FJE-2.png}, displayName=Jonatan Englund, active=true, timeZone=Europe/Stockholm, accountType=atlassian}] | 4chat | sanjin.lihovic |  | 2023-01-18 10:49 | sanjin.lihovic | Klart | Klart | 2023-02-06 11:12 | Uppgift | 2023-02-06 11:12 | Sami Nasufovski | GG-36 Real-time messaging (Epic)
GG-48 | Create different user roles (admin, moderator, user) |  | 1 |  |  |  | Medium | [{self=https://4chat.atlassian.net/rest/api/2/user?accountId=624ab2968678e900705d1178, accountId=624ab2968678e900705d1178, avatarUrls={48x48=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624ab2968678e900705d1178/05988c55-ba76-4ea1-8930-521ec9b7ce1a/48, 24x24=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624ab2968678e900705d1178/05988c55-ba76-4ea1-8930-521ec9b7ce1a/24, 16x16=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624ab2968678e900705d1178/05988c55-ba76-4ea1-8930-521ec9b7ce1a/16, 32x32=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624ab2968678e900705d1178/05988c55-ba76-4ea1-8930-521ec9b7ce1a/32}, displayName=barkat alirahimi, active=true, timeZone=Europe/Stockholm, accountType=atlassian}] | 4chat | sanjin.lihovic |  | 2023-01-18 10:49 | sanjin.lihovic | Backlogg | Pågående | 2023-02-09 14:45 | Uppgift | 2023-02-13 11:37 |  | GG-41 Option for user roles (admin, moderator, user) (Epic)
GG-49 | Assign different permissions to each user role (e.g. only admins can delete chat rooms) |  | 1 |  |  |  | Medium |  | 4chat | sanjin.lihovic |  | 2023-01-18 10:49 | sanjin.lihovic | Backlogg | Pågående | 2023-02-13 10:02 | Uppgift | 2023-02-13 10:02 |  | GG-41 Option for user roles (admin, moderator, user) (Epic)
GG-52 | Implement a feature to promote or demote users |  | 1 |  |  |  | Medium |  | 4chat | sanjin.lihovic |  | 2023-01-18 10:50 | sanjin.lihovic | Backlogg | Pågående | 2023-02-13 10:02 | Uppgift | 2023-02-13 10:02 |  | GG-41 Option for user roles (admin, moderator, user) (Epic)
GG-56 | Implement a feature to report offensive messages |  | 1 |  |  |  | Medium |  | 4chat | sanjin.lihovic |  | 2023-01-18 10:50 | sanjin.lihovic | Backlogg | Pågående | 2023-02-13 10:02 | Uppgift | 2023-02-13 10:02 |  | GG-43 Option for filtering profanity (Epic)
GG-70 | Create a user setting where users can block other users |  | 1 |  |  |  | Medium |  | 4chat | sanjin.lihovic |  | 2023-01-18 11:47 | sanjin.lihovic | Backlogg | Pågående | 2023-02-13 10:03 | Uppgift | 2023-02-13 10:03 |  | GG-69 User blocking and reporting options (Epic)
GG-71 | Create a user setting where users can report other users for inappropriate behavior |  | 1 |  |  |  | Medium |  | 4chat | sanjin.lihovic |  | 2023-01-18 11:47 | sanjin.lihovic | Backlogg | Pågående | 2023-02-13 10:03 | Uppgift | 2023-02-13 10:03 |  | GG-69 User blocking and reporting options (Epic)
GG-72 | Create an admin panel where administrators can view and act on reported users |  | 1 |  |  |  | Medium |  | 4chat | sanjin.lihovic |  | 2023-01-18 11:47 | sanjin.lihovic | Backlogg | Pågående | 2023-02-13 10:02 | Uppgift | 2023-02-13 10:02 |  | GG-69 User blocking and reporting options (Epic)
GG-98 | create UI for chatrooms |  | 1 |  | Klart | 2023-02-09 14:43 | Medium | [{self=https://4chat.atlassian.net/rest/api/2/user?accountId=624ab2968678e900705d1178, accountId=624ab2968678e900705d1178, avatarUrls={48x48=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624ab2968678e900705d1178/05988c55-ba76-4ea1-8930-521ec9b7ce1a/48, 24x24=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624ab2968678e900705d1178/05988c55-ba76-4ea1-8930-521ec9b7ce1a/24, 16x16=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624ab2968678e900705d1178/05988c55-ba76-4ea1-8930-521ec9b7ce1a/16, 32x32=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624ab2968678e900705d1178/05988c55-ba76-4ea1-8930-521ec9b7ce1a/32}, displayName=barkat alirahimi, active=true, timeZone=Europe/Stockholm, accountType=atlassian}, {self=https://4chat.atlassian.net/rest/api/2/user?accountId=624ac240258562006fa61ce3, accountId=624ac240258562006fa61ce3, avatarUrls={48x48=https://secure.gravatar.com/avatar/c9124722ce9863b6b54ec2457a8b199d?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FH-3.png, 24x24=https://secure.gravatar.com/avatar/c9124722ce9863b6b54ec2457a8b199d?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FH-3.png, 16x16=https://secure.gravatar.com/avatar/c9124722ce9863b6b54ec2457a8b199d?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FH-3.png, 32x32=https://secure.gravatar.com/avatar/c9124722ce9863b6b54ec2457a8b199d?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FH-3.png}, displayName=Hannes, active=true, timeZone=Europe/Stockholm, accountType=atlassian}] | 4chat | barkat alirahimi | 2023-02-08 09:35 | 2023-01-27 09:41 | barkat alirahimi | Klart | Klart | 2023-02-09 14:43 | Uppgift | 2023-02-09 14:43 | Hannes | GG-27 Public and private chat rooms (Epic)
GG-105 | Create tests for Public and private chat rooms |  | 1 | purple |  |  | Medium |  | 4chat | M0ller |  | 2023-02-06 15:50 | M0ller | Create Tests | Pågående | 2023-02-13 09:54 | Uppgift | 2023-02-13 09:54 |  | GG-27 Public and private chat rooms (Epic)
GG-106 | Create tests for Real-time messaging |  | 1 | purple |  |  | Medium |  | 4chat | M0ller |  | 2023-02-06 15:51 | M0ller | Create Tests | Pågående | 2023-02-13 09:54 | Uppgift | 2023-02-13 09:54 |  | GG-36 Real-time messaging (Epic)
GG-107 | Create tests for Ability to block other users |  | 1 | purple |  |  | Medium |  | 4chat | M0ller |  | 2023-02-06 15:51 | M0ller | Create Tests | Pågående | 2023-02-13 09:54 | Uppgift | 2023-02-13 09:54 |  | GG-38 Ability to block other users (Epic)
GG-108 | Create tests for Option for user roles |  | 1 | purple |  |  | Medium |  | 4chat | M0ller |  | 2023-02-06 15:52 | M0ller | Create Tests | Pågående | 2023-02-13 09:54 | Uppgift | 2023-02-13 09:54 |  | GG-41 Option for user roles (admin, moderator, user) (Epic)
GG-112 | Create tests for User blocking and reporting |  | 1 | purple |  |  | Medium |  | 4chat | M0ller |  | 2023-02-06 15:52 | M0ller | Create Tests | Pågående | 2023-02-13 09:54 | Uppgift | 2023-02-13 09:54 |  | GG-69 User blocking and reporting options (Epic)
GG-114 | Create tests for Ability to join or create chat rooms |  | 1 | purple |  |  | Medium |  | 4chat | M0ller |  | 2023-02-06 15:53 | M0ller | Create Tests | Pågående | 2023-02-13 09:54 | Uppgift | 2023-02-13 09:54 |  | GG-76 Ability to join or create chat rooms based on topics or interests (Epic)
GG-116 | Create tests for Customizable user settings |  | 1 | purple |  |  | Medium |  | 4chat | M0ller |  | 2023-02-06 15:53 | M0ller | Create Tests | Pågående | 2023-02-13 09:54 | Uppgift | 2023-02-13 09:54 |  | GG-81 Customizable user settings and preferences (Epic)
GG-118 | Implement the functionality of reading in commands through the message inputfield |  | 1 |  | Klart | 2023-02-17 09:28 | Medium | [{self=https://4chat.atlassian.net/rest/api/2/user?accountId=624d3ebbad6b7e006aa8e709, accountId=624d3ebbad6b7e006aa8e709, avatarUrls={48x48=https://secure.gravatar.com/avatar/76357a8ddb2f28a045762b6633b21cde?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FJE-2.png, 24x24=https://secure.gravatar.com/avatar/76357a8ddb2f28a045762b6633b21cde?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FJE-2.png, 16x16=https://secure.gravatar.com/avatar/76357a8ddb2f28a045762b6633b21cde?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FJE-2.png, 32x32=https://secure.gravatar.com/avatar/76357a8ddb2f28a045762b6633b21cde?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FJE-2.png}, displayName=Jonatan Englund, active=true, timeZone=Europe/Stockholm, accountType=atlassian}, {self=https://4chat.atlassian.net/rest/api/2/user?accountId=6234574862dc1e006803bcaf, accountId=6234574862dc1e006803bcaf, avatarUrls={48x48=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/6234574862dc1e006803bcaf/3828a609-73bc-4a61-8bae-3c9d468de4c4/48, 24x24=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/6234574862dc1e006803bcaf/3828a609-73bc-4a61-8bae-3c9d468de4c4/24, 16x16=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/6234574862dc1e006803bcaf/3828a609-73bc-4a61-8bae-3c9d468de4c4/16, 32x32=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/6234574862dc1e006803bcaf/3828a609-73bc-4a61-8bae-3c9d468de4c4/32}, displayName=M0ller, active=true, timeZone=Europe/Stockholm, accountType=atlassian}] | 4chat | Jonatan Englund | 2023-02-15 10:30 | 2023-02-07 12:51 | Jonatan Englund | Klart | Klart | 2023-02-17 09:28 | Uppgift | 2023-02-17 09:29 | M0ller | GG-27 Public and private chat rooms (Epic)
GG-119 | Implement user setting for frontend and ability to change password/email/username |  | 1 | purple | Klart | 2023-02-16 13:52 | Medium | [{self=https://4chat.atlassian.net/rest/api/2/user?accountId=624ab2968678e900705d1178, accountId=624ab2968678e900705d1178, avatarUrls={48x48=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624ab2968678e900705d1178/05988c55-ba76-4ea1-8930-521ec9b7ce1a/48, 24x24=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624ab2968678e900705d1178/05988c55-ba76-4ea1-8930-521ec9b7ce1a/24, 16x16=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624ab2968678e900705d1178/05988c55-ba76-4ea1-8930-521ec9b7ce1a/16, 32x32=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/624ab2968678e900705d1178/05988c55-ba76-4ea1-8930-521ec9b7ce1a/32}, displayName=barkat alirahimi, active=true, timeZone=Europe/Stockholm, accountType=atlassian}, {self=https://4chat.atlassian.net/rest/api/2/user?accountId=626f8f8da1de4100684ecb89, accountId=626f8f8da1de4100684ecb89, avatarUrls={48x48=https://secure.gravatar.com/avatar/739adc12ae3d7abb23402f074af78ffb?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FMH-3.png, 24x24=https://secure.gravatar.com/avatar/739adc12ae3d7abb23402f074af78ffb?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FMH-3.png, 16x16=https://secure.gravatar.com/avatar/739adc12ae3d7abb23402f074af78ffb?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FMH-3.png, 32x32=https://secure.gravatar.com/avatar/739adc12ae3d7abb23402f074af78ffb?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FMH-3.png}, displayName=Måns Hammarsntrad, active=true, timeZone=Europe/Stockholm, accountType=atlassian}, {self=https://4chat.atlassian.net/rest/api/2/user?accountId=624add63f813eb00692c4690, accountId=624add63f813eb00692c4690, avatarUrls={48x48=https://secure.gravatar.com/avatar/f91d28f06f38e0f8f4754152cae13281?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FYJ-5.png, 24x24=https://secure.gravatar.com/avatar/f91d28f06f38e0f8f4754152cae13281?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FYJ-5.png, 16x16=https://secure.gravatar.com/avatar/f91d28f06f38e0f8f4754152cae13281?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FYJ-5.png, 32x32=https://secure.gravatar.com/avatar/f91d28f06f38e0f8f4754152cae13281?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FYJ-5.png}, displayName=Yusupha Jow, active=true, timeZone=Europe/Stockholm, accountType=atlassian}] | 4chat | M0ller | 2023-02-13 09:56 | 2023-02-08 09:32 | M0ller | Klart | Klart | 2023-02-16 13:52 | Uppgift | 2023-02-16 13:52 | Yusupha Jow | GG-81 Customizable user settings and preferences (Epic)
GG-120 | Fix token assignment through frontend |  | 1 |  | Klart | 2023-02-13 09:53 | Medium | [{self=https://4chat.atlassian.net/rest/api/2/user?accountId=624d3ebbad6b7e006aa8e709, accountId=624d3ebbad6b7e006aa8e709, avatarUrls={48x48=https://secure.gravatar.com/avatar/76357a8ddb2f28a045762b6633b21cde?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FJE-2.png, 24x24=https://secure.gravatar.com/avatar/76357a8ddb2f28a045762b6633b21cde?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FJE-2.png, 16x16=https://secure.gravatar.com/avatar/76357a8ddb2f28a045762b6633b21cde?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FJE-2.png, 32x32=https://secure.gravatar.com/avatar/76357a8ddb2f28a045762b6633b21cde?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FJE-2.png}, displayName=Jonatan Englund, active=true, timeZone=Europe/Stockholm, accountType=atlassian}, {self=https://4chat.atlassian.net/rest/api/2/user?accountId=6234574862dc1e006803bcaf, accountId=6234574862dc1e006803bcaf, avatarUrls={48x48=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/6234574862dc1e006803bcaf/3828a609-73bc-4a61-8bae-3c9d468de4c4/48, 24x24=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/6234574862dc1e006803bcaf/3828a609-73bc-4a61-8bae-3c9d468de4c4/24, 16x16=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/6234574862dc1e006803bcaf/3828a609-73bc-4a61-8bae-3c9d468de4c4/16, 32x32=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/6234574862dc1e006803bcaf/3828a609-73bc-4a61-8bae-3c9d468de4c4/32}, displayName=M0ller, active=true, timeZone=Europe/Stockholm, accountType=atlassian}, {self=https://4chat.atlassian.net/rest/api/2/user?accountId=5f5201acfdc3f5003f4f396d, accountId=5f5201acfdc3f5003f4f396d, avatarUrls={48x48=https://secure.gravatar.com/avatar/639a996f196a64b934573ac4b854ed59?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FSN-3.png, 24x24=https://secure.gravatar.com/avatar/639a996f196a64b934573ac4b854ed59?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FSN-3.png, 16x16=https://secure.gravatar.com/avatar/639a996f196a64b934573ac4b854ed59?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FSN-3.png, 32x32=https://secure.gravatar.com/avatar/639a996f196a64b934573ac4b854ed59?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FSN-3.png}, displayName=Sami Nasufovski, active=true, timeZone=Europe/Stockholm, accountType=atlassian}] | 4chat | Sami Nasufovski | 2023-02-11 16:38 | 2023-02-09 09:19 | Sami Nasufovski | Klart | Klart | 2023-02-13 09:53 | Uppgift | 2023-02-13 09:53 | M0ller
GG-121 | Create protected routes component |  | 1 |  | Klart | 2023-02-15 09:54 | Medium |  | 4chat | Hannes |  | 2023-02-09 10:12 | Hannes | Klart | Klart | 2023-02-15 09:54 | Uppgift | 2023-02-15 09:54 | Hannes
GG-122 | Route every room to a specific url |  | 1 |  | Klart | 2023-02-15 09:54 | Medium |  | 4chat | Jonatan Englund |  | 2023-02-13 10:04 | Jonatan Englund | Klart | Klart | 2023-02-15 09:54 | Uppgift | 2023-02-15 09:54 | sanjin.lihovic
GG-123 | Manage the #home room page |  | 1 |  | Klart | 2023-02-17 09:30 | Medium |  | 4chat | Jonatan Englund |  | 2023-02-13 10:04 | Jonatan Englund | Klart | Klart | 2023-02-17 09:30 | Uppgift | 2023-02-17 09:30
GG-124 | Make sure so that messages are being forwarded to the right room and only that room (socket solutions?) |  | 1 |  | Klart | 2023-02-17 09:31 | Medium | [{self=https://4chat.atlassian.net/rest/api/2/user?accountId=624d3ebbad6b7e006aa8e709, accountId=624d3ebbad6b7e006aa8e709, avatarUrls={48x48=https://secure.gravatar.com/avatar/76357a8ddb2f28a045762b6633b21cde?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FJE-2.png, 24x24=https://secure.gravatar.com/avatar/76357a8ddb2f28a045762b6633b21cde?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FJE-2.png, 16x16=https://secure.gravatar.com/avatar/76357a8ddb2f28a045762b6633b21cde?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FJE-2.png, 32x32=https://secure.gravatar.com/avatar/76357a8ddb2f28a045762b6633b21cde?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FJE-2.png}, displayName=Jonatan Englund, active=true, timeZone=Europe/Stockholm, accountType=atlassian}, {self=https://4chat.atlassian.net/rest/api/2/user?accountId=5f5201acfdc3f5003f4f396d, accountId=5f5201acfdc3f5003f4f396d, avatarUrls={48x48=https://secure.gravatar.com/avatar/639a996f196a64b934573ac4b854ed59?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FSN-3.png, 24x24=https://secure.gravatar.com/avatar/639a996f196a64b934573ac4b854ed59?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FSN-3.png, 16x16=https://secure.gravatar.com/avatar/639a996f196a64b934573ac4b854ed59?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FSN-3.png, 32x32=https://secure.gravatar.com/avatar/639a996f196a64b934573ac4b854ed59?d=https%3A%2F%2Favatar-management--avatars.us-west-2.prod.public.atl-paas.net%2Finitials%2FSN-3.png}, displayName=Sami Nasufovski, active=true, timeZone=Europe/Stockholm, accountType=atlassian}] | 4chat | Jonatan Englund | 2023-02-15 10:26 | 2023-02-13 10:05 | Jonatan Englund | Klart | Klart | 2023-02-17 09:31 | Uppgift | 2023-02-17 09:31
GG-125 | Make sure that messages are being logged and stored in the database | * Select message based on room_id * Post * Delete * Update * | 1 |  | Klart | 2023-02-17 09:28 | Medium | [{self=https://4chat.atlassian.net/rest/api/2/user?accountId=6234574862dc1e006803bcaf, accountId=6234574862dc1e006803bcaf, avatarUrls={48x48=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/6234574862dc1e006803bcaf/3828a609-73bc-4a61-8bae-3c9d468de4c4/48, 24x24=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/6234574862dc1e006803bcaf/3828a609-73bc-4a61-8bae-3c9d468de4c4/24, 16x16=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/6234574862dc1e006803bcaf/3828a609-73bc-4a61-8bae-3c9d468de4c4/16, 32x32=https://avatar-management--avatars.us-west-2.prod.public.atl-paas.net/6234574862dc1e006803bcaf/3828a609-73bc-4a61-8bae-3c9d468de4c4/32}, displayName=M0ller, active=true, timeZone=Europe/Stockholm, accountType=atlassian}] | 4chat | Jonatan Englund | 2023-02-16 08:52 | 2023-02-13 10:06 | Jonatan Englund | Klart | Klart | 2023-02-17 09:28 | Uppgift | 2023-02-17 09:28 | M0ller
GG-126 | Look over the functionality of joining rooms and leaving rooms (frontend) |  | 1 |  | Klart | 2023-02-15 10:24 | Medium |  | 4chat | Jonatan Englund | 2023-02-15 10:05 | 2023-02-13 10:08 | Jonatan Englund | Klart | Klart | 2023-02-15 10:24 | Uppgift | 2023-02-16 13:52
GG-127 | Create a clear localstorage on signout in the back-end. |  | 1 |  | Klart | 2023-02-16 13:52 | Medium |  | 4chat | M0ller | 2023-02-15 10:33 | 2023-02-15 09:15 | M0ller | Klart | Klart | 2023-02-16 13:52 | Uppgift | 2023-02-16 13:52 | sanjin.lihovic
GG-128 | Print message in the log when creating a room / leaving / joining.. |  | 1 |  | Klart | 2023-02-17 09:29 | Medium |  | 4chat | M0ller | 2023-02-17 09:29 | 2023-02-15 10:16 | M0ller | Klart | Klart | 2023-02-17 09:29 | Uppgift | 2023-02-17 09:29 | sanjin.lihovic
GG-129 | implementera Webbserver? https |  | 1 |  | Klart | 2023-02-16 13:52 | Medium |  | 4chat | M0ller |  | 2023-02-15 10:20 | M0ller | Klart | Klart | 2023-02-16 13:52 | Uppgift | 2023-02-16 13:52 | Hannes
GG-131 | Build the project succesfully |  | 1 |  | Klart | 2023-02-17 09:30 | Medium |  | 4chat | M0ller |  | 2023-02-15 10:22 | M0ller | Klart | Klart | 2023-02-17 09:30 | Uppgift | 2023-02-17 09:30
GG-132 | Skapa en controller i front-end där vi sätter expoterade funktioner som joinRoom / deleteRoom osv. |  | 1 |  |  |  | Medium |  | 4chat | M0ller |  | 2023-02-15 10:33 | M0ller | Att göra | Att göra | 2023-02-17 09:30 | Uppgift | 2023-02-17 09:30
Created at 18/feb/23 1:01 em by M0ller with Better Excel Exporter for Jira Cloud
help »